## Retrospective Ideas
Feedback From: | Type: | Description: | Evidence: | Actions:
Project team | Went well | tablets installed and working | he guests got the hang of the tablets and that payments worked for the most part. | Tablet installation
Project team | Needs improvement | improve table turn time. | The table tourn time stayed the same | make improvements on table tourn
Project team | Needs improvement | orders that got sent back | survey outcomes | improve tablets with take notes on the side
Project team | Needs improvement | Technical issues during the POS integration process. | There will always be routine maintenance issues that pop up | update the process manual
Project team | Went well | weekly calls with vendors helped us stay on track and clarify task dependencies | survey data and analysis
Project team | Needs improvement | Incrementations of partecipsnts for the birthday party | We didn’t get many participants for the birthday club | update the content on the website and the tablets so it’s clearer what the program is
Project team | Needs improvement | take a look at the waitstaff training process | Staff blame one another if issues come up. | Sharing experiences about how the front of house works, and how the back of house works.