## Tasks and Timeline
Sauce & Spoon Project Plan
Task | Notes | Start Date | Due Date | Duration | Task Owner | Status | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
Define di final requirements of the tablet | Technical specifications, functionality, target user | 2026-05-01 | 2026-05-05 | 4 | PM | NS | bar: WEEK 1 M to WEEK 1 R
Select and confirm the tablet supplier | Cost assessment, quality. delivery time | 2026-05-06 | 2026-05-10 | 4 | PROCUREMENT TEAM | NS | bar: WEEK 1 F to WEEK 2 W
Finalize the hardware and software design of the tablet |  | 2026-05-11 | 2026-05-18 | 7 | PRODUCT TEAM | NS | bar: WEEK 2 R to WEEK 3 F
Produce a batch of tablets for initial tests |  | 2026-05-19 | 2026-05-25 | 6 | ENGINEERING TEAM | NS | bar: WEEK 4 M to WEEK 5 M
Perform quality and functionlity tests on the tablet | Perforamance, security, usability | 2026-05-26 | 2026-06-02 | 7 | ENGINEERING TEAM | NOT STARTED | bar: WEEK 5 T to WEEK 6 W
Collect and Analyze test feedback |  | 2026-06-03 | 2026-06-07 | 4 | QA TEAM | NS | bar: WEEK 6 R to WEEK 7 T
Make changes and improvements based on tets results |  | 2026-06-08 | 2026-06-13 | 5 | PM | NS | bar: WEEK 7 W to WEEK 8 T
Plaan the tablet distribution logistics | shipments, warehouse, timing | 2026-06-14 | 2026-06-20 | 6 | LOGISTIC TEAM | NS | bar: WEEK 8 W to WEEK 9 W
Prepare the support material and documentation | User manuals, guides, technicial support | 2026-06-21 | 2026-06-28 | 7 | CUSTOMER SUPPORT TEAM | NS | bar: WEEK 9 R to WEEK 10 F
Coordinate the official launch of the tablet | stakeholders alignment, communication, release date | 2026-06-29 | 2026-07-02 | 3 | PM | NS | bar: WEEK 11 M to WEEK 11 W
0

## Task Brainstorm
Task Brainstorm
Task | Notes | Estimated Duration (Days) | Optimistic | Most Likely | Pessimistic | Confidence Rating (H/M/L) | Known Dates
1 MILESTONE: IMPLEMENTATION OF NEW SOFTWARE
Prepare the support material and documentation | Includes functional and performance tests | 6 | 5 | 6 | 8 | H | TBD
Introduce waitstaff into new initiative having them buy-in |  | 7 | 5 | 8 | 10
Definition of core features (browse menu, allergens, upsell) |  | 9 | 6 | 9 | 12
Basic ordering flows |  | 4 | 2 | 4 | 7
2 MILESTONE: PLANNING THE IMPLEMENTATION OF THE NEW SOFTWARE
Produce a batch of tablets for initial tests | Requires stakeholder | 6 | 5 | 6 | 7 | M | TBD
Plan the tablet distribution logistics | depnds on stakeholder | 6 | 5 | 5 | 6 | H | TBD
Select and confirm the tablet supplier | Stakeholder input required | 4 | 3 | 4 | 5 | H | TO BE DETERMINATE
Perform quality and functionlity tests on the tablet | Requires stakeholder | 7 | 5 | 6 | 7 | H | TBD
Define a training session group divided in two small groups at time
3 MILESTONE: FINALIZING SUCCESS CRITERIA
Success KPIs (AOV, order time)
Finalize the hardware and software design of the tablet | require Engeineer support | 6 | 5 | 6 | 8 | M | TBD
Define di final requirements of the tablet | Stakeholder input required | 4 | 3 | 4 | 6 | H | TBD
4 MILESTONE: PROJECT LAUNCH
Invite friends and family to test the tablets befoure the official launch |  | 5 | 4 | 5 | 8
Collect and Analyze test feedback | Depends on customer | 3 | 2 | 3 | 5 | L | TBD
Make changes and improvements based on tets results | Depends on feedback | 4 | 3 | 4 | 5 | M | TBD
Coordinate the official launch of the tablet | Depends on vendor and team | 3 | 1 | 2 | 5 | M | TBD
Shipping and reciving tablets |  | 10 days | 7 days | 10 days | 15 days
upload contet for menu items | Waiting on Carther for the finalized menu and coupon value mock-ups for upload | 9 days | 7 days | 10 | 14 | L
upload mock-ups | Once mock-ups are received, 3-4 hours to upload | 4 hours | 2 hours | 3 hours | 5 hours | M
syncronize tablets with POS system |  | 6 hours | 2 hours | 4 hours | 1 day
Update POS systems | Is Possible need to upgrade the POS system if S&S is running an older version | 3 Days | 2 days | 5 days | 7 days
Revamping menu |  | 12 dys | 10 days | 12 days | 14 days
Wiring both locations by electrician | since we can’t close the restaurants for a full day we need to schedule two half-days at each location | 20 hours (3 days) | 16 hours (2 days ) | 5 days | 8 days | H
Fully training the staff | The team has high rate estimate with never attempted integrated tablet software with POS, training waitstuff on new software system, regurarly udate menu via software. they attemped one instead writing with tablets, and they attemped regurarly staff training | 15 days | 10 days | 14 days | 21 days | H

## Additional Resources
Additional Resources
Title | Link | Date Added | Notes
Quality assurance team |  | TBD
Logistics and supply chain documentation |  | TBD
Vendor contracts and pricing agreements |  | TBD
Testing tools and software |  | TBD
Customer support guidelines |  | TBD
Historical projects data from previous tablet launches |  | TBD
Email forewarded to me |  | TBD
https://dinemetrics.de/features/tablet-based-pos?utm_source=chatgpt.com
https://chatgpt.com/?utm_source=microsoft&utm_medium=paidsearch_brand&utm_campaign=MSFT_C_SEM_BBR_Core_CHT_BAU_ACQ_PER_MIX_ALL_EMEA_IT_EN_110625&utm_term=chat%20gpt&utm_content=1179777966712039&utm_ad=&utm_match=e&msclkid=0d285a03a8451f9699f73353a1cc1d62#:~:text=touchscreen%20per%20ristoranti.-,Men%C3%B9%20digitali%20per%20ristoranti%20(METRO%20Italia),-Se%20vuoi%2C%20posso

## Quality and Evaluation
Quality and Evaluation
Quality Standards | Quality Standards
Category | Criteria/Description | Evaluation Questions | Evaluation Indicators | Criteria Met?
Tablet meets all technical requirements and specifications |  |  |  | FALSE
All quality tests completed with accetable results |  |  |  | FALSE
Issues identified during testing are resolved |  |  |  | FALSE
Stakeholder approval obtained before launch |  |  |  | FALSE
Tablet is delivered on time and within budget |  |  |  | FALSE
FALSE
FALSE
COMMITMENT TO CUSTOMER SATISFACTION | safely assume that customers would be satisfied by a faster, more efficient experience | How can we improve? | we can improve by our customer satisfaction, with tablets that will work the way their supposed to and with a decrease customer wait time in the lobby | FALSE
| Customers have their orders made correctly | Which goals are being met? | Goals are being met are training staff, the commitment of customer satisfaction from the team, tablet deliveries and implementation of new orders online. | FALSE
| Customers gìhave good average ticket time | What are the costs and benefits? | the cost is in toto about $50.550, the expense will be worth it because the outcomes from the costs are high in compny improvement such as: the training materials and fee, hardware and software implementation across locations, maintainance, the update design and menu design fee, plkus we took in account even some other unexpected expenses that could pop up during the project lyfe cycle. | FALSE
| Customer will have quicker check out |  |  | FALSE
| Having tablets that works the way their supposed to |  |  | FALSE
| Decrease customer wait time in the lobby |  |  | FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE

## Survey Questions
Survey Questions
Quality Standards |  |  |  |  | Question Answer Options (depends on question type)
Criteria/Description | Evaluation Questions | Evaluation Indicators | Survey Question | Question Type | Option #1 | Option #2 | Option #3 | Option #4 | Option #5
How satisfied are you with the tablet's performance?
Is the tablet easy to use and intuitive?
Did the tablet meet your expectations?
What features could be improved?
Would you recommend this tablet to others?
Tablet meets all technical requirements and specifications
All quality tests completed with accetable results
Issues identified during testing are resolved
Stakeholder approval obtained before launch
Tablet is delivered on time and within budget
COMMITMENT TO CUSTOMER SATISFACTION | safely assume that customers would be satisfied by a faster, more efficient experience | How can we improve? | we can improve by our customer satisfaction, with tablets that will work the way their supposed to and with a decrease customer wait time in the lobby
| Customers have their orders made correctly | Which goals are being met? | Goals are being met are training staff, the commitment of customer satisfaction from the team, tablet deliveries and implementation of new orders online.
| Customers gìhave good average ticket time | What are the costs and benefits? | the cost is in toto about $50.550, the expense will be worth it because the outcomes from the costs are high in compny improvement such as: the training materials and fee, hardware and software implementation across locations, maintainance, the update design and menu design fee, plkus we took in account even some other unexpected expenses that could pop up during the project lyfe cycle.
Customer will have quicker check out
Having tablets that works the way their supposed to
Decrease customer wait time in the lobby
|  |  | How long it took our customer the dining experience? | Open-ended | The dining experience for each customer took 35 minutes
|  |  | On a scale of 1 to 10 how our customer are satisfied? | Scaled | 8
|  |  | Did our customer have a quick checkout? | Yes/No | Yes
|  |  | On a scale of 1 to 5 how our customer are satisfied about the waiting time? | Scaled | 4
|  |  | Customer had a good avarage ticket time | True/False | true
|  |  | Did the tablets met the customer expectations? | Yes/No | yes
|  |  | Did the customer ordered entrees with the tablets? | Open-ended | Customers ordered entrees and also appetizers with the new implementation of tablets
|  |  | how many issues did we have with tablets during the dining experience? | Multiple choice | some issues we faced during the service are: slow connection, customer couldn't customize their orders, and some tablets weren't able to open the payment list.
|  |  | Did we decrease customer wait time in the lobby? | Yes/No | yes
|  |  | Are the tablets ease to use? | Yes/No | yes
|  |  | On a scale of 1 to 10 how our customer gudje the tablet's implememntation? | Scaled | 10