# PROJECT CLOSE-OUT REPORT: TABLET INTEGRATION PILOT

Project: Sauce & Spoon Restaurant Technology Upgrade

Prepared by: Roberta Aiello Date: January 8, 2026

## 1. Project Vision

The goal of this project was to modernize the guest experience at Sauce & Spoon by implementing tabletop ordering technology. The pilot aimed to streamline service, reduce wait times, and capture guest data for marketing purposes, while ensuring a high-quality, secure dining experience.

## 2. Methodology

- Sample Size: 50 test participants during a controlled launch.

- Data Collection: Post-dining digital surveys measuring satisfaction, usability, and speed.

- Key Metrics: Order accuracy, UI navigation ease, payment confidence, and marketing conversion rates.

## 3. Key Accomplishments

- Massive Marketing Growth: Achieved a 78% opt-in rate for the digital newsletter, significantly outperforming previous manual methods.

- High Customer Acceptance: 82% of guests confirmed the checkout process was quick and secure, with a 72% overall positive satisfaction rating.

- Operational Efficiency: 56% of food orders were delivered in under 20 minutes, demonstrating the system's potential to speed up service.

## 4. Lessons Learned

- Kitchen Communication Gap: Identified a 28% error rate in order accuracy, specifically regarding special instructions/modifications that were missed by the kitchen.

- UI/UX Refinement: Only 20% of users rated navigation as "Very Easy," indicating a need to simplify the menu hierarchy to reduce user friction.

- Technical Stability: A 12% glitch/freeze rate was observed, highlighting the need for a hardware and Wi-Fi stability audit before a full-scale rollout.

## 5. Strategic Next Steps

- KDS Optimization: Improve the visibility of "Special Instructions" on the Kitchen Display System to reduce order errors.

- UI/UX Redesign: Streamline the ordering flow to reduce the number of clicks required to add items.

- Incentive Update: Revise the "Birthday Club" offer to increase its low conversion rate (16%) to match the newsletter's success.

- Hybrid Training: Develop a standardized "waiter-plus-tablet" service model to cater to the 30% of guests who prefer a mix of technology and human interaction.